## DD Request Tracker
ID | Category | Request Item | Status | Owner | Data Room Location | Notes
F-01 | Financial | 3-Year Projections | Completed | CEO | 01_Financials/Master_Model_V5.xlsx
F-02 | Financial | Bank Statements (Last 12m) | Pending | Finance | - | Waiting for accountant
L-01 | Legal | Cap Table | Completed | CEO | 01_Financials/Herramientas_V3.xlsx
L-02 | Legal | Incorporation Docs | Completed | Legal | 02_Legal/Documentacion_V2.docx
T-01 | Tech | Architecture Diagram | Completed | CTO | 05_Technical/Tech_Brief.docx
T-02 | Tech | Pentest Report | In Progress | CTO | - | Vendor scheduled for next week
C-01 | Commercial | Top 10 Customers Contracts | Pending | Sales | - | Redacting sensitive info
H-01 | HR | Key Employee Agreements | Completed | HR | 09_Talent/Key_Hires_JDs.docx