## Resumen
Refactoring Plan - Production Code
Generado el 24 de November de 2025
Métricas Extraídas
Lineas | 268
Porcentajes | 100

## Secciones
Sección | Nivel | Contenido | Tablas
Refactoring Plan - Production Code | 1 | **Date**: 2025-01-27 **Status**: Analysis Complete - Ready for Implemen --- | 0
Executive Summary | 2 | This document outlines a comprehensive refactoring | 0
Key Issues Identified | 3 | 1. **Duplicate Utility Files** (3 instances of `ap 2. **Import Inconsistencies** (mixed import paths) 3. **Multiple API Entry Points** (3 different file | 0
Refactoring Goals | 2 | 1. **Eliminate Code Duplication**: Consolidate dup 2. **Standardize Imports**: Use consistent import 3. **Align with Architecture**: Follow the documen | 0
Detailed Refactoring Tasks | 2 |  | 0
Phase 1: Utility Files Consolidation | 3 |  | 0
1.1 Consolidate `api_utils.py` Files | 4 | **Current State:** - `api_utils.py` (root, 268 lines) - Tensor valida - `core/api_utils.py` (231 lines) - FastAPI/Flask | 0
Phase 2: API Entry Points Consolidation | 3 |  | 0
2.1 Unify API Entry Points | 4 | **Current State:** - `api_unified.py` (1237 lines) - Full API impleme - `application.py` (122 lines) - Application facto | 0
Phase 3: Import Path Standardization | 3 |  | 0
3.1 Standardize Import Paths | 4 | **Current Issues:** - Mixed imports: `from api_utils import ...` vs `f - Inconsistent use of root-level imports vs. modul | 0
CORRECT - Use module paths | 1 | from api.api_utils import validate_episode_data from core.api_utils import create_fastapi_app from core.config_manager import ConfigManager | 0
INCORRECT - Root-level imports (deprecated) | 1 | from api_utils import validate_episode_data from config_manager import ConfigManager **Files to Update:** | 0
Phase 4: Config Manager Consolidation | 3 |  | 0
4.1 Resolve Config Manager Duplication | 4 | **Current State:** - `config_manager.py` (root, 521 lines) - `core/config_manager.py` (mentioned in README bu | 0
Phase 5: Directory Structure Alignment | 3 |  | 0
5.1 Resolve `code/` Directory Naming Conflict | 4 | **Current Issue:** - `code/` directory conflicts with Python's built- - Causes import issues when torch tries to import | 0
5.2 Move Root-Level Files to Appropriate Layers | 4 | **Files to Consider Moving:** **To `api/` (Presentation Layer):** - `api_auth.py` → `api/auth.py` (already exists, c | 0
Phase 6: Architecture Alignment | 3 |  | 0
6.1 Ensure Layered Architecture Compliance | 4 | **Current Architecture (from ARCHITECTURE.md):** Presentation (api/, api_*.py, cli*.py, dashboard.h ↓ | 0
Detailed File Analysis | 2 |  | 0
Files Requiring Immediate Attention | 3 |  | 0
High Priority | 4 | 1. **`api_unified.py`** (1237 lines) - **Issue**: Doesn't use new `api/routes/` structu - **Action**: Migrate endpoints to `api/routes/` o | 0
Medium Priority | 4 | 4. **`api_auth.py`** (root, 313 lines) - **Issue**: May duplicate `api/auth.py` - **Action**: Check for duplication, consolidate i | 0
Low Priority | 4 | 7. **Documentation files** - **Action**: Update references to moved/renamed f - **Files**: `README.md`, `ARCHITECTURE.md`, `docs | 0
Implementation Checklist | 2 |  | 0
Phase 1: Utility Consolidation | 3 | - [ ] Analyze differences between three `api_utils - [ ] Migrate root `api_utils.py` functions to `ap - [ ] Update all imports from root `api_utils` | 0
Phase 2: API Consolidation | 3 | - [ ] Compare endpoints in `api_unified.py` vs. `a - [ ] Migrate missing endpoints to `api/routes/` - [ ] Update `application.py` to include all route | 0
Phase 3: Import Standardization | 3 | - [ ] Create import standards document - [ ] Update all root-level imports to module path - [ ] Run linter to verify no root-level imports r | 0
Phase 4: Config Manager | 3 | - [ ] Check if `core/config_manager.py` exists - [ ] Compare functionality if both exist - [ ] Consolidate into `core/config_manager.py` | 0
Phase 5: Directory Structure | 3 | - [ ] Rename `code/` to `code_modules/` - [ ] Update all imports - [ ] Move `api_auth.py` to `api/auth.py` (if not | 0
Phase 6: Architecture Verification | 3 | - [ ] Verify presentation layer imports - [ ] Verify application layer imports - [ ] Verify domain layer imports | 0
🧪 Testing Strategy | 2 |  | 0
Before Refactoring | 3 | 1. Run full test suite to establish baseline 2. Document current behavior 3. Create integration tests for critical paths | 0
During Refactoring | 3 | 1. Run tests after each phase 2. Fix any broken imports immediately 3. Verify functionality hasn't changed | 0
After Refactoring | 3 | 1. Run full test suite 2. Run linter (ruff, mypy) 3. Check for circular imports | 0
Documentation Updates | 2 |  | 0
Files to Update | 3 | 1. **`README.md`** - Update import examples - Update entry point instructions | 0
Risks and Mitigation | 2 |  | 0
Risk 1: Breaking Changes | 3 | - **Risk**: Changing imports may break existing co - **Mitigation**: - Use compatibility shims during transition | 0
Risk 2: Lost Functionality | 3 | - **Risk**: Consolidation may lose some functional - **Mitigation**: - Comprehensive comparison before consolidation | 0
Risk 3: Import Cycles | 3 | - **Risk**: Reorganization may create circular imp - **Mitigation**: - Follow layered architecture strictly | 0
Migration Timeline | 2 |  | 0
Week 1: Analysis & Planning | 3 | - Complete file comparison - Create detailed migration scripts - Set up test baseline | 0
Week 2: Phase 1 & 2 | 3 | - Consolidate utilities - Migrate API endpoints - Update imports | 0
Week 3: Phase 3 & 4 | 3 | - Standardize imports - Consolidate config manager - Update tests | 0
Week 4: Phase 5 & 6 | 3 | - Directory reorganization - Architecture verification - Documentation updates | 0
Week 5: Testing & Cleanup | 3 | - Full test suite - Remove deprecated files - Final documentation | 0
Success Metrics | 2 | 1. **Code Duplication**: Reduce duplicate files to 2. **Import Consistency**: 100% of imports use mod 3. **Architecture Compliance**: All layers follow | 0
Related Documents | 2 | - `ARCHITECTURE.md` - Layered architecture documen - `docs/architecture/layers.md` - Detailed layer r - `CLEANUP_SUMMARY.md` - Previous cleanup efforts | 0
Notes | 2 | - This refactoring should be done incrementally - Maintain backward compatibility during transitio - Use feature flags if needed for gradual rollout | 0

## Gráficas
Categoría | Valor
Líneas | 2